{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":78,"n_cols":30,"rows_kept":78,"cut":false,"hidden":false,"merged":[[60,1,70,1],[57,2,59,2],[51,2,52,2],[53,2,56,2],[48,2,50,2],[60,2,64,2],[75,2,77,2],[9,1,9,2],[39,2,44,2],[45,2,47,2],[29,1,47,1],[15,2,18,2],[10,2,14,2],[10,1,28,1],[19,2,21,2],[22,2,24,2],[25,2,28,2],[71,1,77,1],[29,2,33,2],[34,2,36,2],[37,2,38,2],[48,1,59,1],[34,17,34,18],[36,20,36,21],[65,2,70,2],[71,2,72,2],[73,2,74,2]]}
[]
[]
[]
[{"$nulls":10},"√已完成"]
[]
[]
[]
[{"$nulls":6},"快速查看","睡莲","的工作"]
[]
[null,"分类",null,"项目","负责人","协助","2014-05-28","2014-05-29","2014-05-30","2014-05-31","2014-06-01","2014-06-02","2014-06-03","2014-06-04","2014-06-05","2014-06-06","2014-06-07","2014-06-08","2014-06-09","2014-06-10","2014-06-11","2014-06-12","2014-06-13","2014-06-14","2014-06-15","2014-06-16","2014-06-17","2014-06-18","2014-06-19","2014-06-20"]
[null,"活动相关","预热","会员筛选分类","杜仲","长卿"]
[null,null,null,"制定短信发送计划","苍耳","长卿"]
[null,null,null,"编写短信内容","长卿","苍耳"]
[null,null,null,"为老客户发放优惠券","长卿","杜仲"]
[null,null,null,"预热期间页面发放红包5","长卿","杜仲",{"$nulls":5}," "]
[null,null,"满减","确定满减额度","苍耳","长卿"]
[null,null,null,"优惠券设置","长卿"," "]
[null,null,null,"关联搭配设置","长卿"," "]
[null,null,null,"效果统计","长卿"," "]
[null,null,"最高客单送赠品","制定子活动规则","苍耳"," "]
[null,null,null,"确定产品","苍耳"," "]
[null,null,null,"活动期间发微博艾特老罗","苍耳"]
[null,null,"秒杀","确定秒杀时间","杜仲"]
[null,null,null,"确定秒杀产品","杜仲"]
[null,null,null,"设置秒杀产品库存、价格","杜仲"]
[null,null,"竞猜","选择8支球队 并对应产品","长卿","苍耳"]
[null,null,null,"制定子活动规则","苍耳","长卿"]
[null,null,null,"获奖人员统计","文竹","苍耳"]
[null,null,null,"发放红包","苍耳","长卿"]
[null,"视觉相关","承接页\n（预热期）","demo","长卿","苍耳"]
[null,null,null,"初版","睡莲","葫芦"]
[null,null,null,"讨论","长卿","all"]
[null,null,null,"修改","睡莲","葫芦"]
[null,null,null,"确定","睡莲"," "]
[null,null,"承接页\n（正式） ","demo","长卿","all"]
[null,null,null,"调整","睡莲","葫芦"]
[null,null,null,"最后修订","睡莲","葫芦"]
[null,null,"关联内容","demo","杜仲","all"]
[null,null,null,"页面","睡莲","葫芦"]
[null,null,"其他二级页面","竞猜二级页demo","苍耳","all"]
[null,null,null,"竞猜二级页","睡莲","葫芦"]
[null,null,null,"最高客单二级页demo","苍耳","all"]
[null,null,null,"最高客单二级页","睡莲","葫芦"]
[null,null,null,"秒杀二级页demo","杜仲","all"]
[null,null,null,"秒杀二级页","睡莲","葫芦"]
[null,null,"无线页面","无线页面demo","杜仲"," "]
[null,null,null,"无线页面制作","葫芦","杜仲"]
[null,null,null,"无线相关其他工作","葫芦","杜仲"]
[null,"产品相关","报名","产品阶梯","杜仲"]
[null,null,null,"产品价格确定","苍耳"]
[null,null,null,"产品报名","苍耳"," "]
[null,null,"产品优化","刷好评","杜仲","all"]
[null,null,null,"产品主图补全","杜仲","睡莲"]
[null,null,"校对、准备","产品备货","苍耳"]
[null,null,null,"物料备货","无忧","白桦"]
[null,null,null,"ERP系统校对","无忧","白桦"]
[null,null,null,"校对盘点库存","白桦","无忧"]
[null,null,"赠品","确定大促期间赠品策略","杜仲","长卿"]
[null,null,null,"定制世界杯镜子","苍耳"]
[null,null,null,"定制世界杯手提袋","长卿","苍耳"]
[null,"推广、资源相关","钻展相关","钻展流量需求规划","苍耳","木棉"]
[null,null,null,"钻展投放计划","木棉"]
[null,null,null,"创意图片制作及审核","木棉","睡莲"]
[null,null,null,"钻展投放","木棉","nobody",{"$nulls":9},"测试"]
[null,null,null,"数据总结","木棉"]
[null,null,"资源相关","分会场报名","苍耳"]
[null,null,null,"争取主会场资源","苍耳","景天"]
[null,null,null,"争取无线端资源","苍耳"," "]
[null,null,null,"争取品牌方资源支持","苍耳","景天"]
[null,null,null,"站外活动资源寻找","杜仲","长卿"]
[null,null,null,"联合互换流量活动","景天","苍耳"]
[null,"客服相关","人员安排","客服排班","文竹","苍耳"]
[null,null,null,"培训运营成员","文竹"]
[null,null,"活动通告","运营发送预热通告","长卿"]
[null,null,null,"运营发送活动通告","长卿"]
[null,null,"客服准备","客服熟悉活动","文竹"]
[null,null,null,"设置快捷短语","文竹"]
[null,null,null,"活动资料培训","文竹"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}