{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":28,"n_cols":25,"rows_kept":28,"cut":false,"hidden":false,"merged":[[1,6,1,24],[1,0,3,0],[4,0,27,0],[1,1,3,1],[1,2,3,2],[1,3,3,3],[1,4,3,4],[5,4,11,4],[16,4,20,4],[1,5,3,5]]}
[null,null,null,"618年终大促工作进度总表"]
["5月10日-6月29日","分工项目","注意事项","完成时间","执行人","实际完成情况","5月"]
[{"$nulls":8},"六","日",{"$nulls":5},"六","日",{"$nulls":5},"六","日"]
[{"$nulls":6},5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23]
["运营部","活动跟进 总指挥",null,"5月10日起...","总监"]
[null,"618活动方案确定","年中大促 方向",null,"各店铺负责人"]
[null,"年中大促主题","根据官方来进行"]
[null,"目标规划分解、免费、付费流量","从客单价、UV、广告费投入费用、订单量"]
[null,"618活动各店方案","方案各个细节点操作完善最终版","5月23"]
[null,"活动项确定","大促 活动 抽奖 包年 活动规则"]
[null,"活动后 方案","大促后 返场活动方案"]
[null,"年终大促 商品提报","商品报名到 系统 库存 价格复查"]
[null,"备货数量 初稿","根据业绩规划后测算出 主打款和次打款的备货量和618活动价格，确定后需要提早让工厂准备入仓"]
[null,"物流公司确定","选择多加快递合作汇通圆通 申通 汇通 天天"]
[null,"618奖励政策设定","奖励机制"]
[null,"公司动员大会","完成目标奖励 旅游及现金，具体细节等领导制定，公司营造年终大促氛围 拉横幅，冲劲！"]
[null,"客服小号增加","确定开小号的数量，如有兼职必须管控好权限",null,"各店铺负责人"]
[null,"无线端 页面优化","主推产品无线页面优化方案（8-10款）"]
[null,"活动前店铺的各项检查","618预热前的图片 连接 价格 库存 承接页面 优惠券测试 ERP对接"]
[null,"数据监控","会场入口图的点击测试，店铺首页商品图的点击，运营数据，销售数据全面监控"]
[null,"618临时库存添加","根据活动销售库存情况，适当添加"]
[null,"紧急预案","断电 断网 ERP系统的文档确定（断电，断网要做好客服随时回家或者去网吧上线）"]
[null,"售罄标识","活动当天可以稍留若干售罄标识，增加促销气氛"]
[null,"其他事项"]
[null,"预热店铺页面布局方案","PC 无线 预热店铺页面布局方案"]
[null,"推广费","推广费用提前做预算"]
[null,"直通车 钻展图","经过侧图 直通车图点击率2.0 钻展图点击率5.0的设计图"]
[null,"手机素材","618好素材的收集，收集连接"]