{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":18,"n_cols":32,"rows_kept":18,"cut":false,"hidden":false,"merged":[[0,2,0,20],[0,21,0,31],[1,5,1,9],[1,12,1,16],[1,19,1,20],[1,22,1,23],[1,26,1,30],[0,0,3,0],[0,1,3,1],[4,1,8,1],[9,1,12,1],[13,1,15,1],[16,1,17,1]]}
["时间\n                          工作事项","事项负责人","2015-12-01",{"$nulls":18},"2016-01-01"]
[null,null,"方案确定",null,null,"杂项准备期",{"$nulls":6},"页面设计期",{"$nulls":6},"页面定稿期",null,null,"预审及发信息",null,null,null,"活动期"]
[null,null,"13日","14日","15日","16日","17日","18日","19日","20日","21日","22日","23日","24日","25日","26日","27日","28日","29日","30日","31日","1日","2日","3日","4日","5日","6日","7日","8日","9日","10日","11日"]
[null,null,"星期五","星期六","星期日","星期一","星期二","星期三","星期四","星期五","星期六","星期日","星期一","星期二","星期三","星期四","星期五","星期六","星期日","星期一","星期二","星期三","星期四","星期五","星期六","星期日","星期一","星期二","星期三","星期四","星期五","星期六"]
["确定方案","XX"]
["筛选数据库，确定会员数"]
["确定EDM发送方和数量"]
["确定补偿支付方式和流程"]
["联系商家，说明方案"]
["确认补偿金额及方式","XX"]
["建立新链接，发布宝贝"]
["采购统一店铺优惠券工具"]
["提供选品及宝贝链接"]
["制作活动方案，规划CPS","XX"]
["开始页面设计-邮件正文、独网banner、详情页说明banner"]
["提供设计稿文件给到邮件发送方"]
["发送第一轮邮件：领优惠+收藏","待定"]
["发送第二轮邮件：当天提示活动开始"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}